## Slide 1
Polarion → SysML v2
21 October 2026 → 16 April 2027
26 weeks · one developer · from a blank repository

## Slide 2
THE TARGET
What we are building
end state
one chain, measured
Requirements in, a validated model out — with a typed representation in the middle that everything can be checked against.
Polarion
requirements · links · structure
Ingest
cache · strip · map
Extract
one call per requirement
IR
the contract
Render & update
deterministic · idempotent
SysML v2 model
files · API JSON
Cameo
one-way export, Polarion id attached
Traceability report
every work item: status, elements, findings
PowerPoint · Word · SharePoint
later phase
Existing Cameo model
harvested for grounding
Entity registry
one component, one part — not four
Validation · five layers
IR schema · SysML syntax · architecture consistency · extraction · update
repair loop · agentic · capped
findings go back for that one requirement
Dataset · metrics · MLflow
Every run measured against hand-written expected answers, attributable to a model and a prompt, and replayable without calling the model again.
Solid: inside the 26-week programme. Dashed: a later phase.

## Slide 3
Timeline
26 weeks · 14 workstreams
Oct 2026
Nov
Dec
Jan 2027
Feb
Mar
Apr
Kickoff and scope
W1
Intermediate representation
W2-3
SysML transcription + consistency
W4-6
Dataset generation
W7-9
Christmas · experiment tracking
W10-11
Metrics and evaluation
W12
Extraction
W13-14
Repair loop + evaluation
W15-16
Polarion ingest
W17-19
Entity registry and resolution
W20-21
Model update
W22
Cameo export
W23
Hardening and pilot
W24-25
Buffer and handover
W26
pipeline
agentic
Cameo
reduced capacity
26 calendar weeks → 23.7 engineer-weeks
Christmas ≈ half a week of capacity · Easter costs 26 and 29 March

## Slide 4
PHASE 1 OF 5
Foundation
W1 - W6
21 Oct - 27 Nov 2026
Nothing here involves an LLM. The schema is the contract; get it signed off.
W1
21-23 Oct 2026
Kickoff and scope
Pick the 20-50 requirements for the dataset; book the MBSE engineer.
DONE WHEN
Requirement ids written down, MBSE time in a calendar.
W2-3
26 Oct - 6 Nov
Intermediate representation
Pydantic schema, cross-reference validation, V1/V2 scope boundary — defined with the MBSE engineer. Same sessions: agree the architecture consistency rules. “What makes a model inconsistent in your world?” costs nothing extra while they are already in the room.
DONE WHEN
The MBSE engineer has signed off the schema and a written list of consistency rules. It is the contract between extraction and rendering — everything downstream breaks if it changes later.
W4-6
9 - 27 Nov
SysML transcription + consistency
IR → .sysml, deterministic output, the validator wired into CI, plus the architecture consistency rules agreed in W2-3.
DONE WHEN
A hand-built IR renders and validates with zero diagnostics, in CI, no LLM involved. A deliberately inconsistent IR is rejected with a named reason per problem.

## Slide 5
PHASE 2 OF 5
Dataset and measurement
W7 - W12
30 Nov - 8 Jan
The expected answers, and the thing that scores them — both before anything generates.
W7-9
30 Nov - 18 Dec
Dataset generation
Hand-written IR for the W1 requirements: limits, interfaces, ranges, negatives and non-modelables. Every entry rendered and validated as it is written.
DONE WHEN
30-50 requirements with reviewed expected IR, all validating, usable as a test fixture.
W10-11
21 Dec - 1 Jan 2027
Christmas · experiment tracking
Budget half a week. MLflow, file-backed, plus langchain autolog. Self-contained, needs no LLM and no service — the right kind of holiday work.
DONE WHEN
A run logs its params (model, prompt hash, dataset version, git SHA), its metrics and its artifacts, and the MLflow UI shows it.
W12
4 - 8 Jan
Metrics and evaluation
Subject accuracy, attribute and constraint precision/recall, modelable correctness, validation pass rate. Built against the dataset, before there is an extractor to flatter.
DONE WHEN
Scores the dataset against itself at 100%, a deliberately corrupted copy below that. Re-scoring an earlier run from its traces works without calling the LLM.

## Slide 6
PHASE 3 OF 5
The model
W13 - W16
11 Jan - 5 Feb
How hard are our requirements, actually? First real answer, with nine weeks left to react.
W13-14
11 - 22 Jan
Extraction
One structured-output LLM call per requirement.
DONE WHEN
The dataset runs end to end and produces IR without hand-editing. The W12 harness prints a baseline on the first run.
W15-16
25 Jan - 5 Feb
Repair loop + evaluation
The one agentic element: a conditional edge back to extraction, fed the IR validation errors and consistency findings for that one requirement, retry-capped. The second week is evaluation — does it help, and does it ever harm?
DONE WHEN
Pass rate and repair iterations before and after, on the dataset. The cap is never silently exceeded. No requirement scores worse after repair than before, measured against the expected IR.

## Slide 7
PHASE 4 OF 5
Integration
W17 - W23
8 Feb - 26 Mar
Real requirements in, a model out, and the second run is an update rather than a replacement.
W17-19
8 - 26 Feb
Polarion ingest
Auth, paging, caching, link roles, HTML stripping, work item → IR mapping. Populate Trace.revision, which W22 needs as its change signal.
DONE WHEN
Real work items produce a validated model with a hardcoded registry and no LLM. Every requirement carries its Polarion revision.
W20-21
1 - 12 Mar
Entity registry and resolution
Seed from Polarion components or the product breakdown; merge “the pump” / “pump unit” / “P-101” into one part.
DONE WHEN
Subject resolution rate against an agreed target, no duplicate part def for a known entity, registry seeded rather than hand-written, and two runs produce identical names.
W22
15 - 19 Mar
Model update
Stable element identity, change detection against the previous run, and a diff report. Not a full merge into hand-edited models.
DONE WHEN
Running twice on unchanged input produces an empty diff. Changing one requirement produces a diff naming exactly that requirement and the elements it touches.
W23
22 - 26 Mar
Cameo export
One-way, whichever route the early spike picked. Manual import is an acceptable outcome. Karfreitag 26 Mar — four days.
DONE WHEN
Generated content opens in Cameo, correctly typed, with the Polarion id attached.

## Slide 8
PHASE 5 OF 5
Landing
W24 - W26
29 Mar - 16 Apr
Someone other than the author runs it, on the real project.
W24-25
29 Mar - 9 Apr
Hardening and pilot
Full real project, failure modes, run it with an engineer watching. Ostermontag 29 Mar — nine days.
DONE WHEN
A full run completes, the report is trustworthy, and someone other than the author has used it.
W26
12 - 16 Apr
Buffer and handover
Documentation, known limitations.
DONE WHEN
Deliberately empty. If it is already spent by February, cut scope instead.